## Sheet1
DETAILED IMPLEMENTATION WORK PLAN
| DETAILED IMPLEMENTATION ACTIVITY | IN-CHARGE | ESTIMATED NO. OF MAN DAYS |  |  |  | ESTIMATED TIMELINE
|  |  | TOTAL | REALTY | FINANCIALS | PM | START DATE | END DATE
1 | Meeting with PPHI for the review of data setup; Identification of setups/records that will also be loaded in the new company database | FPTI/PPHI | 3 | 1 | 1 | 1
2 | Back up and Restoration of PPHI Database to new/clean company databases (with FPTI pre-loaded data/setup) | FPTI | 1 | -- | -- | --
3 | Data Migration and Clean-up based from the identified setups/records that will also be loaded for the new company database from the restored PPHI Database (Access, COA, Terms of Payments, etc.) | FPTI | 5.5 | 1.5 | 2 | 2
4 | Data Quality Check of the uploaded data in the new company database | FPTI | 2.5 | 0.5 | 1 | 1
5 | User Validation of the uploaded data in the new company database | PPHI | -- | -- | -- | --
6 | User Training | FPTI/PPHI | 10 | 2 | 5 | 3
7 | Post-Implementation Support | FPTI | 8 | -- | -- | --
|  |  | 30 | 5 | 9 | 7

## Sheet1 (2)
DETAILED IMPLEMENTATION WORK PLAN
| DETAILED IMPLEMENTATION ACTIVITY | IN-CHARGE | GALLERY | MODULE/PROCESS | ESTIMATED NO. OF MAN DAYS | ESTIMATED TIMELINE
[6 empty] | START DATE | END DATE
1 | Meeting with PPHI for the review of data setup; Identification of setups/records that will also be loaded in the new company database | FPTI/PPHI | REALTY | RE Inventory, RE Sales and Booking (with Special Transactions) | 0.5 | 2021-06-24 | 2021-06-24
|  |  |  | Document Control, RE Billing and Collection and RE Broker Management | 0.5 | 2021-06-25 | 2021-06-25
|  |  | FINANCIALS | Systems Global, General Ledger, Purchase Order and Financials Inventory | 0.5 | 2021-06-28 | 2021-06-28
|  |  |  | Property, Plant and Equipment, Accounts Payable and Cash Management | 0.5 | 2021-06-29 | 2021-06-29
|  |  | PM | Project Build-up, and Project Stages and Hierarchy | 0.5 | 2021-06-30 | 2021-06-30
|  |  | PM | Item Master, BOM/BOQ and Sub Location/ Warehouse | 0.5 | 2021-07-01 | 2021-07-01
2 | Back up and Restoration of PPHI Database to new/clean company databases (with FPTI pre-loaded data/setup) | FPTI | REALTY |  | 1 | 2021-07-29 | 2021-07-29
FINANCIALS
PM
3 | Data Migration and Clean-up based from the identified setups/records that will also be loaded for the new company database from the restored PPHI Database (Access, COA, Terms of Payments, etc.) | FPTI | REALTY |  | 1.5 | 2021-08-03 | 2021-08-04
|  |  | FINANCIALS |  | 2 | 2021-08-03 | 2021-08-04
|  |  | PM |  | 2 | 2021-08-04 | 2021-08-05
4 | Data Quality Check of the uploaded data in the new company database | FPTI | REALTY |  | 0.5 | 2021-08-04 | 2021-08-04
|  |  | FINANCIALS |  | 1 | 2021-08-05 | 2021-08-05
|  |  | PM |  | 1 | 2021-08-06 | 2021-08-06
5 | User Validation of the uploaded data in the new company database (Direct Setups should also be populated by PHDC) | PPHI | REALTY |  |  | 2021-08-09 | 2021-08-11
FINANCIALS
PM
6 | User Training | FPTI/PPHI | REALTY | RE Inventory and Document Control Compliance | 0.5 | 2021-08-12 | 2021-08-12
|  |  |  | RE Sales and Booking and RE Billing and Collection | 0.5 | 2021-08-12 | 2021-08-12
|  |  |  | RE Broker Management and Titling | 0.5 | 2021-08-13 | 2021-08-13
|  |  |  | RE Special Transactions | 0.5 | 2021-08-13 | 2021-08-13
|  |  | FINANCIALS | Systems Admin and Systems Global | 1 | 2021-08-16 | 2021-08-16
|  |  |  | General Ledger and Purchase Order | 1 | 2021-08-17 | 2021-08-17
|  |  |  | Financials Inventory and Property, Plant and Equipment | 1 | 2021-08-18 | 2021-08-18
|  |  |  | Accounts Payable | 1 | 2021-08-19 | 2021-08-19
|  |  |  | Cash Management | 1 | 2021-08-20 | 2021-08-20
|  |  | PM | PM Setups, Project Budget and Project Timeline | 1 | 2021-08-23 | 2021-08-23
|  |  |  | Material Requirements Planning to Receiving | 1 | 2021-08-24 | 2021-08-24
|  |  |  | Issuance and Transfer of Stocks | 1 | 2021-08-25 | 2021-08-25
7 | GO LIVE | FPTI/PPHI | REALTY |  |  | 2021-08-30 | Onwards
FINANCIALS
PM
8 | Post-Implementation Support | FPTI | REALTY |  | 8 | 2021-08-30 | Onwards
FINANCIALS
PM
30

## Sheet2 (hidden)
1 | Prepare the Detailed Workplan for the New Company (Per Module)
2 | Include the estimated no. Of mandays for each activities